## Sheet1
Project Plan
Thesis: |  | Real-Time Rendering of Translucent Materials with Directional Subsurface Scattering
Student: |  | Alessandro Dal Corso
Student number: |  | s120929
Week Number |  |  | Planned Activities | Details
week 6 | 2014-02-03 | 2014-02-09 | Literature study | Cascaded Light Propagation Volumes [Kaplanyan et. Al.] - studied approach to lattice-based translucency. Also looked at [Børlum et al.] with a possible approach with SSLPV (Subsurface Scattering Light Propagation Volumes)
week 7 | 2014-02-10 | 2014-02-16 | Literature study | Numerical validation of the model simulating it on a python-based simulation framework. Started comparison of the studied models in order to decide which one is the best way to go.
week 8 | 2014-02-17 | 2014-02-23 | Implementation | Choice of the actual method. Basic implementation on the chosen framework of some auxiliary classes (Materials, Lights, SH calculation routines). Start research on the actual rendering method
week 9 | 2014-02-24 | 2014-03-02 | Implementation | Code: Configured debugger, added basic point light/directional light system, refactored the framework to be more general. Started implementing version of Directional Dipole. Works on planes, to test on spheres.
Theory: Tried to devise a numerical condition to optimize shader calculations (if distance more than d, discard contribution)
Writing: Updated introduction, corrected some mistakes, added references and an image.
week 10 | 2014-03-03 | 2014-03-09 | Implementation | Code: Trying to apply the naïve method to spheres and cubes (works but with banding artifact), then extending to general geometry (probably works, but needs testing). Start implementation of conservative rasterization, first step of the method (no time).
Writing: Writing summary of related work section, with the most relevant papers outlined. (needs some additions still)
week 11 | 2014-03-10 | 2014-03-16 | Implementation | Code: Implemented naïve implementation on CPU with the base Jensen et al. dipole and the Better Dipole by D'Eon et al. directional dipole shows some overshooting
Writing: Finishing related work section
week 12 | 2014-03-17 | 2014-03-23 | Implementation | Implementing initial part of my method (reasoning how to do that)
Writing: Related Works
week 13 | 2014-03-24 | 2014-03-30 | Implementation | Basic implementation continuing
week 14 | 2014-03-31 | 2014-04-06 | Implementation | Eventual extensions of implementation (different types of lights, heterogenous materials…)
week 15 | 2014-04-07 | 2014-04-13 | Validation and optimization | Eventual extensions of implementation (different types of lights, heterogenous materials…)
week 16 | 2014-04-14 | 2014-04-20 | Validation and optimization | Low level optimization of the code/shaders
week 17 | 2014-04-21 | 2014-04-27 | Validation and optimization
week 18 | 2014-04-28 | 2014-05-04 | Validation and optimization | Comparison with naïve method on different conditions.
week 19 | 2014-05-05 | 2014-05-11 | Validation and optimization | Timing comparisons with other existing methods.
week 20 | 2014-05-12 | 2014-05-18 | Validation and optimization
week 21 | 2014-05-19 | 2014-05-25 | Writing | Started final writing of the thesis (reordering notes taken throughout the thesis). Introduction chapters and previous work.
week 22 | 2014-05-26 | 2014-06-01 | Writing | Description of our actual method.
week 23 | 2014-06-02 | 2014-06-08 | Writing | Description of our actual method.
week 24 | 2014-06-09 | 2014-06-15 | Writing | Results and validation.
week 25 | 2014-06-16 | 2014-06-22 | Writing | Results and validation.
week 26 | 2014-06-23 | 2014-06-29 | Writing | Reharsal.
week 27 | 2014-06-30 | 2014-07-06 | Final Handin week