## Sheet1
Project Plan
Thesis: |  |  | Real-Time Rendering of Translucent Materials with Directional Subsurface Scattering
Student: |  |  | Alessandro Dal Corso
Student number: |  |  | s120929
Week Number |  |  | Planned Activities | Details
week 6 | 2014-02-03 | 2014-02-09 | Literature study | Cascaded Light Propagation Volumes [Kaplanyan et. Al.] - studied approach to lattice-based translucency. Also looked at [Børlum et al.] with a possible approach with SSLPV (Subsurface Scattering Light Propagation Volumes)
week 7 | 2014-02-10 | 2014-02-16 | Literature study | Numerical validation of the model simulating it on a python-based simulation framework. Started comparison of the studied models in order to decide which one is the best way to go.
week 8 | 2014-02-17 | 2014-02-23 | Implementation | Choice of the actual method. Basic implementation on the chosen framework of some auxiliary classes (Materials, Lights, SH calculation routines). Start research on the actual rendering method
week 9 | 2014-02-24 | 2014-03-02 | Implementation | Code: Configured debugger, added basic point light/directional light system, refactored the framework to be more general. Started implementing version of Directional Dipole. Works on planes, to test on spheres.
Theory: Tried to devise a numerical condition to optimize shader calculations (if distance more than d, discard contribution)
Documents: Updated introduction, corrected some mistakes, added references and an image.
week 10 | 2014-03-03 | 2014-03-09 | Implementation | Trying to apply the naïve method to spheres and cubes, then extending to general geometry. Start implementation of conservative rasterization, first step of the method.
week 11 | 2014-03-10 | 2014-03-16 | Implementation | Continuing implementation of the rendering method.
week 12 | 2014-03-17 | 2014-03-23 | Implementation | Concluding basic implementation.
week 13 | 2014-03-24 | 2014-03-30 | Implementation | Eventual extensions of implementation (different types of lights, heterogenous materials…)
week 14 | 2014-03-31 | 2014-04-06 | Implementation | Eventual extensions of implementation (different types of lights, heterogenous materials…)
week 15 | 2014-04-07 | 2014-04-13 | Validation and optimization | Low level optimization of the code/shaders
week 16 | 2014-04-14 | 2014-04-20 | Validation and optimization
week 17 | 2014-04-21 | 2014-04-27 | Validation and optimization | Comparison with naïve method on different conditions.
week 18 | 2014-04-28 | 2014-05-04 | Validation and optimization | Timing comparisons with other existing methods.
week 19 | 2014-05-05 | 2014-05-11 | Validation and optimization
week 20 | 2014-05-12 | 2014-05-18 | Validation and optimization
week 21 | 2014-05-19 | 2014-05-25 | Writing | Started final writing of the thesis (reordering notes taken throughout the thesis). Introduction chapters and previous work.
week 22 | 2014-05-26 | 2014-06-01 | Writing | Description of our actual method.
week 23 | 2014-06-02 | 2014-06-08 | Writing | Description of our actual method.
week 24 | 2014-06-09 | 2014-06-15 | Writing | Results and validation.
week 25 | 2014-06-16 | 2014-06-22 | Writing | Results and validation.
week 26 | 2014-06-23 | 2014-06-29 | Writing | Reharsal.
week 27 | 2014-06-30 | 2014-07-06 | Final Handin week